## Master Register
PROJECT-WIDE SIGN-OFF TRACKER — MASTER REGISTER
Skye Fundraising Intelligence Dashboard · All required approvals across the full project lifecycle · March 15, 2026
Sign-Off ID | Category | Deliverable / Decision | Required Approver(s) | Secondary Approver | Due Date | Signed Date | Status | Version | Blocking? | Document Ref | Notes / Conditions | RAG
SO-BR-001 | Brand & Strategy | Brand Name — Skye Data Advisory | Founder / Principal | — | Pre-launch | — | PENDING | v1.0 | YES | Chat history | Name selected; no formal sign-off document exists
SO-BR-002 | Brand & Strategy | Brand Brief — Colors, Fonts, Logo Direction | Founder / Principal | Marketing Lead | Pre-launch | — | PENDING | v1.0 | NO | DGO-001 Ref | Brand brief produced; stakeholder approval not documented
SO-BR-003 | Brand & Strategy | Tagline — 'Data strategy, analytics, and governance for mission-driven organizations' | Founder / Principal | — | Pre-launch | — | PENDING | v1.0 | NO | Chat history | Final tagline not formally confirmed
SO-BR-004 | Brand & Strategy | Color System — Final 8-color palette including Signal Coral | Founder / Principal | UX Lead | Pre-launch | — | PENDING | v1.0 | NO | Dashboard Design Guide | Coral selected; no written confirmation
SO-DA-001 | Analytics Design | Analytics Use Case Statement — Fundraising Intelligence | Business Owner | DGO | Before build | — | PENDING | v1.0 | YES | 03_Analytics_Use_Case_Process | Use case defined in documentation; not signed off
SO-DA-002 | Analytics Design | Metric Definitions — All 9 metrics and Tableau calculations | Business Owner | DGO | Before build | — | PENDING | v1.0 | YES | 02_Data_Dictionary_and_Metric_Definitions | Definitions documented; written sign-off required per process
SO-DA-003 | Analytics Design | Data Dictionary — All 15 fields in DONATIONS_RAW | Business Owner | Fundraising Steward | Before build | — | PENDING | v1.0 | YES | 02_Data_Dictionary | Definitions exist; no formal approval recorded
SO-DA-004 | Analytics Design | Dashboard Tab Structure — 3 tabs approved | Business Owner | UX Lead | Before build | — | PENDING | v1.0 | YES | Wireframe Sign-Off SO-001 | THIS is the current blocker — wireframe sign-off not completed
SO-DA-005 | Analytics Design | Outlier Definition — 2× window average threshold | Business Owner | DGO | Before build | — | PENDING | v1.0 | NO | 02_Data_Dictionary | Threshold defined; not explicitly approved
SO-WF-001 | Wireframes | Tab 1 — Executive Overview wireframe | Business Owner | DGO | Before development | — | PENDING | v1.0 | YES | 01_Wireframe_Sign_Off_Document | OUTSTANDING — blocks Tab 1 development
SO-WF-002 | Wireframes | Tab 2 — Campaign Performance wireframe | Business Owner | DGO | Before development | — | PENDING | v1.0 | YES | 01_Wireframe_Sign_Off_Document | OUTSTANDING — blocks Tab 2 development
SO-WF-003 | Wireframes | Tab 3 — Donor Intelligence wireframe | Business Owner | DGO | Before development | — | PENDING | v1.0 | YES | 01_Wireframe_Sign_Off_Document | OUTSTANDING — blocks Tab 3 development
SO-GOV-001 | Governance | Data Governance Framework — Principles, Roles, Policy | Founder / Principal | Legal / Compliance | Before real data | — | PENDING | v1.0 | YES | 01_Data_Governance_Framework_and_Policy | Framework produced; not signed by leadership
SO-GOV-002 | Governance | Data Ownership Register — All fields and systems assigned | All Stewards | DGO | Before real data | — | PENDING | v1.0 | YES | 02_Data_Ownership_Register | Roles defined; named individuals not yet assigned or signed
SO-GOV-003 | Governance | Data Classification — Tier 1–4 applied to all assets | DGO | Technology Steward | Before real data | — | PENDING | v1.0 | YES | 02_Data_Ownership_Register | Classification scheme defined; not applied or signed
SO-GOV-004 | Governance | Data Quality Scorecard — 20 rules approved | DGO | Business Owner | Before production | — | PENDING | v1.0 | NO | 03_Data_Quality_Scorecard | Rules defined; not yet activated or approved
SO-GOV-005 | Governance | Data Retention Schedule — Periods confirmed | DGO | Legal | Before real data | — | PENDING | v1.0 | YES | 01_Data_Governance_Framework | Schedule defined in framework; not operationalized
SO-COM-001 | Compliance | Snowflake Data Processing Agreement | Technology Steward | Legal | Before real data load | — | PENDING | — | YES | 04_Gap_Analysis GAP-004 | DPA not executed — CRITICAL compliance gap
SO-COM-002 | Compliance | Donor Privacy Policy Review — Analytics use case | DGO | Legal | Before real data | — | PENDING | — | YES | 04_Gap_Analysis GAP-008 | Policy review not completed
SO-COM-003 | Compliance | Tableau Public Publication Policy Acknowledgment | All team members | DGO | Before first publish | — | PENDING | — | YES | 04_Gap_Analysis GAP-005 | No publish approval workflow exists
SO-COM-004 | Compliance | Email Platform Vendor Data Agreement | Technology Steward | Legal | Before email data use | — | PENDING | — | NO | 04_Gap_Analysis GAP-009 | Not yet addressed
SO-TECH-001 | Technical | Snowflake Schema Design — DONATIONS_RAW table structure | Technology Steward | DGO | Before data load | — | PENDING | v1.0 | YES | 04_Snowflake_Tableau_Technical_Guide | Schema defined; no formal sign-off
SO-TECH-002 | Technical | VW_FUNDRAISING_DASHBOARD view definition | Technology Steward | Fundraising Steward | Before Tableau build | — | PENDING | v1.0 | YES | 04_Snowflake_Tableau_Technical_Guide | View SQL documented; not signed off
SO-TECH-003 | Technical | Extract File Naming Convention — v1 format approved | Technology Steward | DGO | Before first export | — | PENDING | v1.0 | NO | Technical Guide | Convention defined; not formally agreed
SO-TECH-004 | Technical | Tableau Calculated Fields — All 11 formulas approved | Business Owner | DGO + Analyst | Before dashboard build | — | PENDING | v1.0 | YES | 05_Tableau_Workbook_Specification | Formulas documented; business approval needed
SO-QA-001 | QA | QA Test Plan — 10 tests and acceptance criteria approved | Business Owner | DGO | Before testing | — | PENDING | v1.0 | YES | 06_Dashboard_QA_Test_Plan | Test plan produced; formal approval not obtained
SO-QA-002 | QA | QA Sign-Off — All 10 tests passed | DGO | Business Owner | After QA, before publish | — | PENDING | — | YES | 06_Dashboard_QA_Test_Plan | Cannot sign off until QA is run; blocked by wireframe sign-off
SO-QA-003 | QA | Usability Test Results — 3 users, 6 questions, <30sec threshold | Business Owner | DGO | After QA | — | PENDING | — | YES | 06_Dashboard_QA_Test_Plan | Usability test not yet conducted
SO-QA-004 | QA | Reconciliation Baseline — Snowflake totals vs Finance System | Fundraising Steward | Technology Steward | Before dashboard build | — | PENDING | — | YES | 06_Dashboard_QA_Test_Plan | Baseline not established for production data
SO-PUB-001 | Publication | Tableau Public Dashboard — Final publication authorization | Business Owner | DGO + Executive Sponsor | Before go-live | — | PENDING | — | YES | Governance Framework | Cannot publish until all RED items above are resolved
SO-PUB-002 | Publication | Consumer Training Delivery — All dashboard users trained | DGO | Project Manager | Before go-live | — | PENDING | — | YES | 04_Gap_Analysis GAP-011 | Training not yet developed or delivered
SO-PUB-003 | Publication | Data Currency Date — Displayed on published dashboard | Technology Steward | DGO | Before go-live | — | PENDING | — | NO | Dashboard Design Guide | Standard practice; to be confirmed at publish
SO-PROD-001 | Product | Skye Data Maturity Accelerator — Product spec approved | Founder / Principal | DGO | Product launch | — | NOT STARTED | — | NO | Chat history | Product planned; spec not built
SO-PROD-002 | Product | Skye Fundraising Intelligence — Product pricing approved | Founder / Principal | — | Product launch | — | NOT STARTED | — | NO | Chat history | Pricing tiers discussed; not formalized
SO-PROD-003 | Product | Demo Dataset — Approved for public portfolio use | DGO | Founder / Principal | Before portfolio publish | — | PENDING | v1.0 | NO | Governance Certification | Demo data is synthetic; DGO conditional approval issued

## Summary Dashboard
SIGN-OFF STATUS SUMMARY
Counts by category and RAG status · March 15, 2026
Category | Total | RED | AMBER | GREEN | % Complete | Notes
Brand & Strategy | 4 | 0 | 4 | 0 | 0% | Name and brief decisions documented; formal sign-offs outstanding
Analytics Design | 5 | 4 | 1 | 0 | 0% | Metric definitions are the critical blocker; business sign-off needed
Wireframes | 3 | 3 | 0 | 0 | 0% | ALL THREE TABS OUTSTANDING — this is the immediate priority
Governance | 5 | 3 | 2 | 0 | 0% | Framework built; ownership register needs named individuals assigned
Compliance | 4 | 3 | 1 | 0 | 0% | Snowflake DPA is the single most urgent compliance gap
Technical | 4 | 2 | 2 | 0 | 0% | Schema and view defined; formal approval needed before production build
QA | 4 | 4 | 0 | 0 | 0% | Cannot begin until wireframes are signed off and Tableau build starts
Publication | 3 | 2 | 1 | 0 | 0% | Blocked by all upstream RED items; publication not yet authorized
Product | 3 | 0 | 2 | 1 | 33.33% | Product roadmap agreed; formal spec and pricing not yet formalized
TOTAL | 35 | 21 | 13 | 1 | 2.857% | GREEN items only: 1 of 35 sign-offs complete

## Immediate Actions
IMMEDIATE ACTION PLAN — Critical Sign-Offs Required NOW
Items that are blocking development or creating compliance risk · March 15, 2026
# | Sign-Off Required | Why It's Blocking | Who Must Act | Deadline | Status
1 | Tab 1, 2, 3 Wireframe Sign-Off (SO-WF-001/002/003) | No development can begin on any Tableau worksheet without this | Business Owner (Dev Director) | This week | OUTSTANDING
2 | Metric Definitions Sign-Off (SO-DA-002) | Metric disputes after build are extremely costly; sign-off prevents scope creep | Business Owner + DGO | Before build starts | OUTSTANDING
3 | Data Ownership Register — Assign Named Individuals (SO-GOV-002) | Without named stewards, there is no accountability chain for data quality issues | DGO + All Stewards | This week | OUTSTANDING
4 | Snowflake DPA — Initiate Legal Process (SO-COM-001) | Cannot legally load real donor data without a Data Processing Agreement | Technology Steward + Legal | Before real data load | OUTSTANDING
5 | Tableau Public Publication Approval Workflow (SO-COM-003) | Risk of accidental PII publication if any team member can publish without approval | DGO | Immediately | OUTSTANDING
6 | Data Classification Applied to All Assets (SO-GOV-003) | Access controls cannot be properly set without classification | DGO | Before real data ingestion | OUTSTANDING
7 | Donor Privacy Policy Review (SO-COM-002) | Analytics use cases may violate donor privacy commitments if not reviewed | DGO + Legal | Before production dashboard | OUTSTANDING
8 | Tableau Calculated Fields Sign-Off (SO-TECH-004) | Silent metric errors are the most damaging type of dashboard failure | Business Owner + Analyst | Before Tableau build | OUTSTANDING