## Test Execution Log
UAT TEST EXECUTION LOG — Skye Fundraising Intelligence Dashboard
Executed by: Business Analyst · Julie Chen (Fundraising) · Chloe Rivera (Marketing) · March 15, 2026
Test ID | Story ID | Tab | Component | Test Description | Tester | Date | Expected Result | Actual Result | Pass/Fail | Defect # | Notes
FT-01a | US-01 | Tab 1 | KPI: Total Donations | Apply full-year 2024 filter → verify Total Donations = $1.24M | Julie Chen | March 15, 2026 | $1,240,000 ± 0.1% | $1,242,315 — within threshold | PASS | — | Matches Snowflake SUM query exactly
FT-01b | US-01 | Tab 1 | KPI: Total Donations | Change Date Range to Q1 → verify KPI updates | BA | March 15, 2026 | KPI changes to Q1 value | Updated to $312,450 in < 1.5s | PASS | — | Filter response time: 0.8s
FT-01c | US-01 | Tab 1 | KPI: Total Donations | Apply Donor Segment = Major → verify KPI filters | Julie Chen | March 15, 2026 | Major-only donations shown | $645,000 — 52% of total | PASS | — | Consistent with segment donut on Tab 3
FT-01d | US-01 | Tab 1 | KPI: Total Donations | Remove all filters → verify full-year value returns | BA | March 15, 2026 | Returns to $1,242,315 | Returned correctly | PASS | —
FT-01e | US-01 | Tab 1 | KPI: Total Donations | Cross-check against Snowflake SUM | BA | March 15, 2026 | < 0.1% variance | 0.04% variance | PASS | — | NFR-009 met
FT-02a | US-02 | Tab 1 | Donor Growth Chart | Verify 12 monthly data points for 2024 | BA | March 15, 2026 | 12 bars + 12 line points | 12 months render correctly | PASS | —
FT-02b | US-02 | Tab 1 | Donor Growth Chart | Verify retention line moves independently on filter | Julie Chen | March 15, 2026 | Line updates independently | Line updated correctly on filter | PASS | —
FT-02c | US-02 | Tab 1 | Donor Growth Chart | Apply Campaign = WHM → verify March spike | Julie Chen | March 15, 2026 | March bar highlighted | Spike visible with Gold annotation | PASS | —
FT-02d | US-02 | Tab 1 | Donor Growth Chart | Verify tooltip on 3 random months | Chloe Rivera | March 15, 2026 | Month + count + retention % | Tooltip shows all 3 values | PASS | — | Chloe confirmed labels clear
FT-02e | US-02 | Tab 1 | Donor Growth Chart | Verify 65% reference line renders | BA | March 15, 2026 | Reference line at 65% | Line renders; labeled '65% target' | PASS | — | NFR-007 met
FT-03a | US-03 | Tab 1 | Revenue by Channel | Verify 4 channels appear | BA | March 15, 2026 | Email, Social, Direct, Event | All 4 present | PASS | —
FT-03b | US-03 | Tab 1 | Revenue by Channel | Verify Email is longest bar (52%) | Chloe Rivera | March 15, 2026 | Email bar = 52% of total | Email bar longest — 52% | PASS | — | Chloe: 'That matches what I'd expect'
FT-03c | US-03 | Tab 1 | Revenue by Channel | Apply Channel = Email only | BA | March 15, 2026 | Single bar shown | Single bar renders correctly | PASS | —
FT-03d | US-03 | Tab 1 | Revenue by Channel | Verify revenue labels at bar end | Chloe Rivera | March 15, 2026 | $ amount at bar end | Labels visible and formatted | PASS | —
FT-04a | US-04 | Tab 1 | Campaign ROI Ranking | Verify WHM is #1 at 6.8x | Chloe Rivera | March 15, 2026 | WHM ranked 1st with 6.8x | 6.8x confirmed — ranked #1 | PASS | —
FT-04b | US-04 | Tab 1 | Campaign ROI Ranking | Verify Gold highlight on top campaign | Chloe Rivera | March 15, 2026 | Top bar in Mission Gold | Gold applied correctly | PASS | — | Chloe approved the color distinction
FT-04c | US-04 | Tab 1 | Campaign ROI Ranking | Verify 1.0x breakeven line | BA | March 15, 2026 | Reference line at 1.0x | Line renders and labeled | PASS | —
FT-04d | US-04 | Tab 1 | Campaign ROI Ranking | Test Coral for loss-making campaign | BA | March 15, 2026 | Loss campaign bar in Coral | Coral applied for ROI < 1.0x | PASS | — | Tested with modified dataset
FT-04e | US-04 | Tab 1 | Campaign ROI Ranking | Verify tooltip: revenue + cost + ROI | Chloe Rivera | March 15, 2026 | 3 values in tooltip | All 3 values present | PASS | — | Chloe: 'This is exactly what I need for my budget conversation'
FT-05a | US-05 | Tab 1 | Insight Annotation Bar | Verify annotation renders at bottom | BA | March 15, 2026 | Green callout bar visible | Renders correctly | PASS | —
FT-05b | US-05 | Tab 1 | Insight Annotation Bar | Verify WHM and retention referenced | Chloe Rivera | March 15, 2026 | Both findings mentioned | Both mentioned — plain English | PASS | —
FT-05c | US-05 | Tab 1 | Insight Annotation Bar | Verify visible without scrolling at 1366px | BA | March 15, 2026 | Visible without scroll | Visible on 1366px | PASS | — | NFR-008 met
FT-05d | US-05 | Tab 1 | Insight Annotation Bar | Verify no overlap with charts | BA | March 15, 2026 | No overlap | Clean separation | PASS | —
FT-06a | US-06 | Tab 2 | Email Funnel | Verify 4 stages with correct labels | Chloe Rivera | March 15, 2026 | Sent, Opened, Clicked, Donated | All 4 stages present | PASS | —
FT-06b | US-06 | Tab 2 | Email Funnel | Verify stage counts and percentages | Chloe Rivera | March 15, 2026 | 22400/8960(40%)/3763(42%)/1190(32%) | All counts and percentages correct | PASS | — | Chloe: 'The 42% click-to-open is very strong. I want to show this to leadership.'
FT-06c | US-06 | Tab 2 | Email Funnel | Apply Campaign filter → verify update | Chloe Rivera | March 15, 2026 | Funnel updates to campaign | Updated correctly for WHM | PASS | —
FT-06d | US-06 | Tab 2 | Email Funnel | Verify % is vs previous stage (not total sent) | BA | March 15, 2026 | Clicked % = clicked/opened | 42% = clicked/opened confirmed | PASS | — | Critical — common funnel mistake to show vs total
FT-06e | US-06 | Tab 2 | Email Funnel | Verify visual narrowing of funnel shape | Chloe Rivera | March 15, 2026 | Visually narrows top to bottom | Narrowing visible and clear | PASS | —
FT-07a | US-07 | Tab 2 | Cost vs Revenue Chart | Verify all campaign pairs render | BA | March 15, 2026 | All pairs with 2 bars each | All pairs render | PASS | —
FT-07b | US-07 | Tab 2 | Cost vs Revenue Chart | Verify Major Donor Event has highest Cost bar | Julie Chen | March 15, 2026 | Cost bar = $20k | $20k Coral bar — tallest cost | PASS | — | Julie: 'This is the conversation I need to have about events vs. direct mail'
FT-07c | US-07 | Tab 2 | Cost vs Revenue Chart | Verify WHM has highest Revenue bar | Julie Chen | March 15, 2026 | Revenue bar = $195k | $195k confirmed | PASS | —
FT-07d | US-07 | Tab 2 | Cost vs Revenue Chart | Verify legend: Navy=Revenue, Coral=Cost | Chloe Rivera | March 15, 2026 | Legend renders correctly | Legend present and correct | PASS | —
FT-08a | US-08 | Tab 2 | Revenue by Campaign | Verify WHM is top bar at $195k | Julie Chen | March 15, 2026 | WHM first, $195k | Confirmed | PASS | —
FT-08b | US-08 | Tab 2 | Revenue by Campaign | Verify Gold on top campaign only | Julie Chen | March 15, 2026 | Only top bar is Gold | Only WHM bar is Gold | PASS | —
FT-08c | US-08 | Tab 2 | Revenue by Campaign | Verify all 9 campaigns appear | BA | March 15, 2026 | 9 campaign bars | All 9 present | PASS | —
FT-08d | US-08 | Tab 2 | Revenue by Campaign | Apply Channel = Email → verify update | Chloe Rivera | March 15, 2026 | Email-only revenue shown | Bars update correctly | PASS | —
FT-09a | US-09 | Tab 3 | Donor Segmentation | Verify 3 segments in bar and 3 donuts | Julie Chen | March 15, 2026 | General/Major/Recurring | All 3 render | PASS | —
FT-09b | US-09 | Tab 3 | Donor Segmentation | Verify Major donut = ~52% in Gold | Julie Chen | March 15, 2026 | Major donut ~52% | 52% — Gold donut | PASS | — | Julie: 'That 52% is the number I reference every single board meeting'
FT-09c | US-09 | Tab 3 | Donor Segmentation | Verify General donut = ~38% in Navy | BA | March 15, 2026 | General ~38% | 38% confirmed | PASS | —
FT-09e | US-09 | Tab 3 | Donor Segmentation | Verify no individual donor data visible | Julie Chen | March 15, 2026 | No names/amounts | No PII visible | PASS | — | Critical governance check — passed
FT-10a | US-10 | Tab 3 | Geographic Map | Verify all 10 demo states present | BA | March 15, 2026 | 10 states with dots | All 10 states visible | PASS | —
FT-10b | US-10 | Tab 3 | Geographic Map | Verify CA shows largest dot | Julie Chen | March 15, 2026 | CA largest dot | CA dot is largest | PASS | —
FT-10c | US-10 | Tab 3 | Geographic Map | Verify tooltip: state + revenue + donors | Julie Chen | March 15, 2026 | 3 values in tooltip | All 3 present | PASS | —
FT-10d | US-10 | Tab 3 | Geographic Map | Apply Major segment → map updates | BA | March 15, 2026 | Map shows major donor states | Updates correctly | PASS | —
FT-10e | US-10 | Tab 3 | Geographic Map | Verify no street/ZIP data visible | BA | March 15, 2026 | State level only | State level only — no ZIP/city | PASS | — | NFR-011 met
FT-11a | US-11 | Tab 3 | Outlier Detection | Verify September in Coral | Julie Chen | March 15, 2026 | Sept dot = Coral | Coral applied to Sept | PASS | —
FT-11b | US-11 | Tab 3 | Outlier Detection | Verify no other Coral data points | BA | March 15, 2026 | Only Sept is Coral | Only Sept — Coral exclusive | PASS | — | NFR-005 met
FT-11c | US-11 | Tab 3 | Outlier Detection | Verify Sept annotation visible | Julie Chen | March 15, 2026 | Plain-English annotation | Annotation visible and clear | PASS | —
FT-11d | US-11 | Tab 3 | Outlier Detection | Exclude Sept via filter → Coral disappears | BA | March 15, 2026 | No Coral when Sept excluded | Coral disappears correctly | PASS | —
FT-12a | US-12 | Tab 3 | Lifetime Giving Histogram | Verify 6 bins with correct labels | Chloe Rivera | March 15, 2026 | 6 bins as specified | All 6 bins render | PASS | —
FT-12b | US-12 | Tab 3 | Lifetime Giving Histogram | Verify $0-1k is tallest bar (~42%) | BA | March 15, 2026 | $0-1k tallest | $0-1k is tallest at ~42% | PASS | —
FT-12c | US-12 | Tab 3 | Lifetime Giving Histogram | Verify $10k+ bins are Gold | Chloe Rivera | March 15, 2026 | Gold on high-value bins | Gold applied to $10-20k and $20k+ | PASS | — | Chloe: 'This tells me our mid-level upgrade pipeline clearly'
FT-12d | US-12 | Tab 3 | Lifetime Giving Histogram | Apply Major segment → bins shift right | BA | March 15, 2026 | Higher bins more prominent | Histogram shifts to right bins | PASS | —
FT-12e | US-12 | Tab 3 | Lifetime Giving Histogram | Verify tooltip: range + count + pct | Chloe Rivera | March 15, 2026 | 3 values in tooltip | All 3 present | PASS | —

## NFR Test Results
NON-FUNCTIONAL REQUIREMENTS TEST RESULTS
Benchmarked against Salesforce NPSP, Blackbaud, Bloomerang, Virtuous, Tableau Public · March 15, 2026
NFR ID | Category | Requirement | Target | Industry Standard | Test Method | Result | Tester | Status
NFR-001 | Performance | Dashboard load time | < 3 seconds | Tableau Public avg: 2-4s | Timed with stopwatch on 50Mbps connection | 2.1 seconds — first load | BA | PASS
NFR-002 | Performance | Filter response time | < 1.5s | Industry BI standard: sub-2s | Applied 5 different filter combinations, timed each | Max 1.3s — all filters | BA | PASS
NFR-003 | Accessibility | Color contrast ratio | WCAG AA: 4.5:1 text; 3:1 charts | Blackbaud, Salesforce: WCAG AA compliant | WebAIM Contrast Checker on all Skye brand color pairs | All pairs meet AA minimum | BA | PASS
NFR-004 | Accessibility | Font size minimums | No text < 9pt; KPI labels ≥ 11pt | Tableau Public default: 10pt | Inspected all labels in published view | All labels ≥ 10pt; KPIs at 14pt | Chloe Rivera | PASS
NFR-005 | Accessibility | Color-blind safe palette | Distinguishable with deuteranopia | Bloomerang: blue/orange only | Coblis color-blindness simulator on all 8 brand colors | All colors distinguishable in deutan/protan modes | BA | PASS
NFR-006 | Usability | Time-to-insight < 30 seconds | < 30s per primary question | Nielsen Norman: 15-45s for expert users | Live test: Julie & Chloe answer 6 questions each | All 12 questions answered in < 25 seconds | Julie + Chloe | PASS
NFR-007 | Usability | Metric tooltips on all KPIs | Every metric has plain-English tooltip | Salesforce NPSP: tooltips on all KPIs | Hovered all 8 KPI cards and 15 charts | All have tooltips; language approved by Julie | Julie Chen | PASS
NFR-008 | Usability | Mobile / tablet responsiveness | Readable on 768px (iPad portrait) | Tableau Public responsive at 768px+ | Tested on iPad Air (Safari) and Chrome DevTools 768px | All 3 tabs readable; KPI cards stack correctly | Chloe Rivera | PASS
NFR-009 | Data Integrity | Metric accuracy | < 0.1% variance vs Finance System | Blackbaud: guarantees ±0; Tableau: ±float rounding | Reconciled all KPI totals against Snowflake SUM queries | Max variance: 0.04% — all within threshold | BA + Julie | PASS
NFR-010 | Data Integrity | Data currency indicator | Timestamp visible on every view | All leading nonprofit platforms show data age | Checked published Tableau view for timestamp presence | Timestamp visible in dashboard footer — 'Data as of [date]' | BA | PASS
NFR-011 | Security | No PII in public view | Zero donor names/emails/addresses | Blackbaud/Salesforce: row-level security enforced | Scanned all 3 tabs; searched for name/email patterns | Zero PII found in any published view | BA + DGO | PASS
NFR-012 | Maintainability | Metric change propagation | One formula edit updates all views | dbt/semantic layer standard | Changed Campaign ROI formula in calculated field; verified all views updated | All 3 ROI views updated with one edit | BA | PASS

## UAT Summary
UAT EXECUTION SUMMARY
| Total Functional Test Cases Executed | 51
| Passed | 51
| Failed | 0
| Blocked | 0
| Deferred | 0
| Pass Rate | 100%
| Total NFR Tests Executed | 12
| NFR Tests Passed | 12
| NFR Pass Rate | 100%
| User Stories Tested | 12
| User Stories Fully Accepted | 12
| Outstanding Defects | 0
| UAT Lead | Business Analyst — Skye Data Advisory
| Fundraising Stakeholder | Julie Chen — Director of Development
| Marketing Stakeholder | Chloe Rivera — Director of Marketing
| Test Execution Date | March 15, 2026
| Recommendation | APPROVE FOR STAKEHOLDER SIGN-OFF