## Master Register (Updated)
PROJECT SIGN-OFF TRACKER — UPDATED WITH STAKEHOLDER SIGN-OFFS
Julie Chen (Fundraising) and Chloe Rivera (Marketing) have signed off · March 15, 2026
Sign-Off ID | Category | Deliverable / Decision | Required Approver(s) | Secondary Approver | Due Date | Signed Date | Status | Version | Blocking? | Signed By | Notes / Conditions | RAG
SO-BR-001 | Brand & Strategy | Brand Name — Skye Data Advisory | Founder / Principal | — | Pre-launch | — | PENDING | v1.0 | YES | — | Name selected; no formal sign-off document exists | AMBER
SO-BR-002 | Brand & Strategy | Brand Brief — Colors, Fonts, Logo Direction | Founder / Principal | Marketing Lead | Pre-launch | — | PENDING | v1.0 | NO | — | Brand brief produced; stakeholder approval not documented | AMBER
SO-BR-003 | Brand & Strategy | Tagline Approval | Founder / Principal | — | Pre-launch | — | PENDING | v1.0 | NO | — | Final tagline not formally confirmed | AMBER
SO-BR-004 | Brand & Strategy | Color System — Final 8-color palette | Founder / Principal | UX Lead | Pre-launch | — | PENDING | v1.0 | NO | — | Coral selected; no written confirmation | AMBER
SO-DA-001 | Analytics Design | Analytics Use Case Statement | Business Owner | DGO | Before build | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | Julie: Signed after reviewing traceability doc. Chloe: Confirmed marketing use cases covered. | GREEN
SO-DA-002 | Analytics Design | Metric Definitions — All 9 metrics | Business Owner | DGO | Before build | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | All 9 metrics reviewed and approved in traceability session. Julie confirmed donor retention definition. Chloe confirmed email conversion definition. | GREEN
SO-DA-003 | Analytics Design | Data Dictionary — All 15 fields | Business Owner | Fundraising Steward | Before build | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen | Julie reviewed all field definitions. Donor_Segment values confirmed: General, Major, Recurring. | GREEN
SO-DA-004 | Analytics Design | Dashboard Tab Structure — 3 tabs approved | Business Owner | UX Lead | Before build | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | SEE WIREFRAME SIGN-OFFS BELOW. Full traceability review completed. Both stakeholders signed. | GREEN
SO-DA-005 | Analytics Design | Outlier Definition — 2x window average threshold | Business Owner | DGO | Before build | March 15, 2026 | SIGNED — APPROVED WITH COMMENTS | v1.0 | NO | Julie Chen | Julie: Approved 2x threshold. Comment: 'Please also flag gifts > $25k individually regardless of window average for major donor review.' | GREEN
SO-WF-001 | Wireframes | Tab 1 — Executive Overview wireframe | Business Owner | DGO | Before development | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | Julie: 'The KPI cards answer exactly what I need for board meetings. Donations trend with March spike annotation is excellent.' Chloe: 'Campaign ROI chart with 6.8x label is exactly the narrative I need.' All 12 checklist items approved. | GREEN
SO-WF-002 | Wireframes | Tab 2 — Campaign Performance wireframe | Business Owner | DGO | Before development | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | Julie: 'Revenue by Campaign sorted view is what I open every Monday morning. Approved.' Chloe: 'Email funnel is the chart I have been asking for. The 42% click-to-open is a strong story. Approved.' One minor comment: Chloe requested clearer funnel percentage labels — logged as C-001. | GREEN
SO-WF-003 | Wireframes | Tab 3 — Donor Intelligence wireframe | Business Owner | DGO | Before development | March 15, 2026 | SIGNED — APPROVED WITH COMMENTS | v1.0 | YES | Julie Chen | Julie: 'Major donor 52% donut is a critical governance metric for me — very clear. Geography map is perfect — state level only is correct.' Comment: Julie requested a 'Year over Year' toggle on the Repeat vs New trend — logged as C-002. Approved to proceed. | GREEN
SO-GOV-001 | Governance | Data Governance Framework | Founder / Principal | Legal / Compliance | Before real data | — | PENDING | v1.0 | YES | — | Framework produced; not signed by leadership | RED
SO-GOV-002 | Governance | Data Ownership Register | All Stewards | DGO | Before real data | — | PENDING | v1.0 | YES | — | Roles defined; named individuals not yet assigned or signed | RED
SO-GOV-003 | Governance | Data Classification Applied | DGO | Technology Steward | Before real data | — | PENDING | v1.0 | YES | — | Classification scheme defined; not applied or signed | RED
SO-GOV-004 | Governance | Data Quality Scorecard — 20 rules | DGO | Business Owner | Before production | — | PENDING | v1.0 | NO | — | Rules defined; not yet activated or approved | AMBER
SO-GOV-005 | Governance | Data Retention Schedule | DGO | Legal | Before real data | — | PENDING | v1.0 | YES | — | Schedule defined; not operationalized | AMBER
SO-COM-001 | Compliance | Snowflake Data Processing Agreement | Technology Steward | Legal | Before real data load | — | PENDING | — | YES | — | DPA not executed — CRITICAL compliance gap | RED
SO-COM-002 | Compliance | Donor Privacy Policy Review | DGO | Legal | Before real data | — | PENDING | — | YES | — | Policy review not completed | RED
SO-COM-003 | Compliance | Tableau Public Publication Policy | All team members | DGO | Before first publish | — | PENDING | — | YES | — | No publish approval workflow exists | RED
SO-COM-004 | Compliance | Email Platform Vendor Data Agreement | Technology Steward | Legal | Before email data use | — | PENDING | — | NO | — | Not yet addressed | AMBER
SO-TECH-001 | Technical | Snowflake Schema Design | Technology Steward | DGO | Before data load | — | PENDING | v1.0 | YES | — | Schema defined; no formal sign-off | AMBER
SO-TECH-002 | Technical | VW_FUNDRAISING_DASHBOARD view definition | Technology Steward | Fundraising Steward | Before Tableau build | — | PENDING | v1.0 | YES | — | View SQL documented; not signed off | AMBER
SO-TECH-003 | Technical | Extract File Naming Convention | Technology Steward | DGO | Before first export | — | PENDING | v1.0 | NO | — | Convention defined; not formally agreed | AMBER
SO-TECH-004 | Technical | Tableau Calculated Fields — All 11 formulas | Business Owner | DGO + Analyst | Before dashboard build | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | All calculated fields reviewed in traceability session. Julie confirmed Repeat Donor Rate formula. Chloe confirmed Email Conversion Rate formula. Both approved. | GREEN
SO-QA-001 | QA | QA Test Plan — 10 tests and acceptance criteria | Business Owner | DGO | Before testing | March 15, 2026 | SIGNED — APPROVED | v1.0 | YES | Julie Chen + Chloe Rivera | QA plan reviewed and approved as part of UAT traceability session. Julie and Chloe served as usability test subjects. | GREEN
SO-QA-002 | QA | QA Sign-Off — All 10 tests passed | DGO | Business Owner | After QA, before publish | March 15, 2026 | SIGNED — APPROVED | — | YES | Julie Chen + Chloe Rivera | 51 functional tests: 51 PASS, 0 FAIL. 12 NFR tests: 12 PASS. All acceptance criteria met. | GREEN
SO-QA-003 | QA | Usability Test — 6 questions in < 30s | Business Owner | DGO | After QA | March 15, 2026 | SIGNED — APPROVED | — | YES | Julie Chen + Chloe Rivera | Julie: All 6 questions answered avg 18 seconds. Chloe: All 6 questions answered avg 22 seconds. NFR-006 passed. | GREEN
SO-QA-004 | QA | Reconciliation Baseline — Snowflake vs Finance | Fundraising Steward | Technology Steward | Before dashboard build | March 15, 2026 | SIGNED — APPROVED | — | YES | Julie Chen | Julie confirmed Total Donations reconciles to Finance System within 0.04% variance. NFR-009 passed. | GREEN
SO-PUB-001 | Publication | Tableau Public Dashboard — Final authorization | Business Owner | DGO + Executive Sponsor | Before go-live | — | PENDING | — | YES | — | Wireframe and UAT sign-offs complete. Governance RED items must close before this can proceed. | AMBER
SO-PUB-002 | Publication | Consumer Training Delivery | DGO | Project Manager | Before go-live | — | PENDING | — | YES | — | Training not yet developed or delivered | RED
SO-PUB-003 | Publication | Data Currency Date on Dashboard | Technology Steward | DGO | Before go-live | — | PENDING | — | NO | — | Standard practice; to be confirmed at publish | AMBER
SO-PROD-001 | Product | Skye Data Maturity Accelerator — Product spec | Founder / Principal | DGO | Product launch | — | NOT STARTED | — | NO | — | Product planned; spec not built | AMBER
SO-PROD-002 | Product | Skye Fundraising Intelligence — Pricing | Founder / Principal | — | Product launch | — | NOT STARTED | — | NO | — | Pricing tiers discussed; not formalized | AMBER
SO-PROD-003 | Product | Demo Dataset — Approved for portfolio use | DGO | Founder / Principal | Before portfolio publish | March 15, 2026 | SIGNED — APPROVED | v1.0 | NO | Julie Chen | Julie confirmed demo dataset contains no real donor data. Approved for Tableau Public portfolio. | GREEN

## Stakeholder Personas & Sign-Off
STAKEHOLDER PERSONAS & FORMAL SIGN-OFF RECORDS
PERSONA 1 — JULIE CHEN
Full Name | Julie Chen
Title | Director of Development & Fundraising
Organization | Skye Data Advisory Client Organization (Nonprofit)
Reports To | Executive Director
Years in Role | 8 years
Primary Concern | Donor retention rate, campaign ROI, major donor concentration
Dashboard Tabs | Primary user of Tab 1 (Executive Overview) and Tab 3 (Donor Intelligence)
UAT Role | Usability test subject, functional test validator, metric definition approver
Sign-Off Authority | Fundraising & Development — Wireframes, Metric Definitions, Data Dictionary, QA
Notable Comments | 'The 52% major donor concentration on Tab 3 is the number I reference every board meeting.' / 'Campaign ROI ranking solves my Monday morning spreadsheet problem.' / 'The September outlier annotation is exactly the kind of data quality flag I need before I walk into a room.'
JULIE CHEN — FORMAL SIGN-OFF RECORD
Sign-Off ID | Deliverable | Decision | Julie's Recorded Comment | Date Signed
SO-WF-001 | Tab 1 — Executive Overview Wireframe | APPROVED | KPI cards and annotation bar answer my board reporting needs exactly. Campaign ROI ranking and Donor Growth dual axis are production-ready. | March 15, 2026
SO-WF-002 | Tab 2 — Campaign Performance Wireframe | APPROVED | Revenue by Campaign sorted view is my primary weekly view. Cost vs Revenue chart gives me the Major Donor Event ROI conversation I need. | March 15, 2026
SO-WF-003 | Tab 3 — Donor Intelligence Wireframe | APPROVED WITH COMMENTS | Major donor 52% donut is critical. Geography map is correct at state level. REQUEST: Add YoY toggle to Repeat vs New trend chart (logged C-002). | March 15, 2026
SO-DA-002 | Metric Definitions — All 9 Metrics | APPROVED | Repeat Donor Rate formula using Donated_More_Than_Once flag confirmed. Campaign ROI using FIXED LOD confirmed. All definitions accurate. | March 15, 2026
SO-DA-003 | Data Dictionary — All 15 Fields | APPROVED | Donor_Segment controlled vocabulary confirmed: General, Major, Recurring. Lifetime_Giving as cumulative value confirmed. | March 15, 2026
SO-QA-002 | UAT — All Tests Passed | APPROVED | Usability test: answered all 6 primary questions in average 18 seconds. All acceptance criteria met. Recommend proceeding to publication. | March 15, 2026
SO-PROD-003 | Demo Dataset — Portfolio Use | APPROVED | Confirmed no real donor data in the synthetic dataset. Safe for Tableau Public portfolio publication. | March 15, 2026
PERSONA 2 — CHLOE RIVERA
Full Name | Chloe Rivera
Title | Director of Marketing & Communications
Organization | Skye Data Advisory Client Organization (Nonprofit)
Reports To | Executive Director
Years in Role | 2 years
Primary Concern | Proving marketing ROI; email funnel conversion; channel attribution
Dashboard Tabs | Primary user of Tab 2 (Campaign Performance); secondary user of Tabs 1 and 3
UAT Role | Usability test subject, email funnel validator, accessibility reviewer
Sign-Off Authority | Marketing & Communications — Wireframes (campaign tab), email metrics, accessibility, brand consistency
Notable Comments | 'Email funnel showing 42% click-to-open is the story I have been trying to tell for 2 years — now I have data.' / 'Campaign ROI chart with Gold on Women's History Month is exactly the visual I need for my budget proposal.' / 'Lifetime giving histogram tells me the size of the mid-level upgrade pipeline instantly.'
CHLOE RIVERA — FORMAL SIGN-OFF RECORD
Sign-Off ID | Deliverable | Decision | Chloe's Recorded Comment | Date Signed
SO-WF-001 | Tab 1 — Executive Overview Wireframe | APPROVED | Campaign ROI ranking with Gold on Women's History Month is a compelling visual story for budget conversations. Annotation bar provides the plain-English context I need. | March 15, 2026
SO-WF-002 | Tab 2 — Campaign Performance Wireframe | APPROVED WITH COMMENTS | Email funnel is the most important chart for my team. Approved. REQUEST: Please add percentage labels directly on funnel stages rather than tooltip-only (logged C-001). | March 15, 2026
SO-WF-003 | Tab 3 — Donor Intelligence Wireframe | APPROVED | Lifetime giving histogram is clear and actionable for upgrade campaigns. Geographic map at state level is appropriate. | March 15, 2026
SO-DA-002 | Metric Definitions — Email Metrics | APPROVED | Email Conversion Rate formula confirmed as click-to-open rate (clicked/opened), not clicked/sent. This distinction matters for reporting. Confirmed and approved. | March 15, 2026
SO-DA-004 | Dashboard Tab Structure — 3 Tabs | APPROVED | Three-tab structure is logical. Tab 2 as dedicated campaign tab ensures marketing data is not buried behind executive overview. | March 15, 2026
SO-QA-002 | UAT — All Tests Passed | APPROVED | Usability test: answered all 6 questions in average 22 seconds. Accessibility checks passed including colorblind simulation. Font sizes meet requirements. Recommend approval. | March 15, 2026
SO-TECH-004 | Tableau Calculated Fields | APPROVED | Email Conversion Rate field confirmed. Campaign ROI FIXED LOD confirmed. All formulas reviewed and approved for development. | March 15, 2026

## Change Requests (From UAT)
CHANGE REQUESTS RAISED DURING STAKEHOLDER SIGN-OFF
Comments logged during Julie Chen and Chloe Rivera wireframe review · March 15, 2026
Comment # | Raised By | Tab | Element | Request | Priority | Owner | Status
C-001 | Chloe Rivera | Tab 2 | Email Engagement Funnel | Add percentage labels directly on funnel stage bars (not tooltip-only). Rationale: Chloe presents this chart live in meetings where tooltips are not visible. | Medium | UX Lead / Tableau Developer | OPEN — scheduled for next sprint
C-002 | Julie Chen | Tab 3 | Repeat vs New Donor Trend | Add a Year-over-Year comparison toggle so current year can be benchmarked against prior year. Rationale: Julie uses YoY comparison in every board presentation. | High | UX Lead / Tableau Developer | OPEN — requires YoY data in dataset; logged for Phase 2
C-003 | Julie Chen | Tab 3 | Outlier Detection | In addition to the 2x window average rule, also flag individual gifts > $25,000 regardless of window context, for major donor review workflow. | Medium | Business Analyst / DGO | OPEN — requires new calculated field; DGO must review before implementation