## Project Status Dashboard
SKYE DATA ADVISORY — FUNDRAISING INTELLIGENCE DASHBOARD
Project Status Dashboard · Build Window: April 15 – May 13, 2026 · Tableau Public
STAKEHOLDER SIGN-OFF STATUS (March 15, 2026)
Sign-Off ID | Deliverable / Decision | Required Approver | Signed Date | Status | Notes
SO-DA-001 | Analytics Use Case Statement | Julie Chen + Chloe Rivera | Mar 15, 2026 | SIGNED ✓ | Both stakeholders confirmed use cases
SO-DA-002 | Metric Definitions — All 9 metrics | Julie Chen + Chloe Rivera | Mar 15, 2026 | SIGNED ✓ | All definitions reviewed; retention & email conversion confirmed
SO-DA-003 | Data Dictionary — 15 fields | Julie Chen | Mar 15, 2026 | SIGNED ✓ | Donor_Segment values confirmed: General, Major, Recurring
SO-DA-004 | Dashboard Tab Structure — 3 tabs | Julie Chen + Chloe Rivera | Mar 15, 2026 | SIGNED ✓ | Full traceability review completed
SO-DA-005 | Outlier Definition — 2x window avg | Julie Chen | Mar 15, 2026 | SIGNED ✓* | Approved with comment: also flag gifts >$25k (C-003)
SO-WF-001 | Wireframe Sign-Off — Tab 1 | Business Owner | Mar 15, 2026 | SIGNED ✓ | All 12 checklist items approved
SO-WF-002 | Wireframe Sign-Off — Tab 2 | Business Owner | Mar 15, 2026 | SIGNED ✓ | All 12 checklist items approved
SO-WF-003 | Wireframe Sign-Off — Tab 3 | Business Owner | Mar 15, 2026 | SIGNED ✓ | All 12 checklist items approved
SO-BR-001 | Brand Name — Skye Data Advisory | Founder / Principal | — | PENDING ⚠ | No formal sign-off document exists
SO-BR-002 | Brand Brief — Colors, Fonts, Logo | Founder / Principal | — | PENDING ⚠ | Brief produced; approval not documented
UAT EXECUTION RESULTS (March 15, 2026)
Metric | Result | Target | Status
Functional Test Cases Executed | 51 | 51 | PASS ✓
Functional Tests Passed | 51 | 51 | PASS ✓
Functional Tests Failed | 0 | 0 | PASS ✓
NFR Tests Executed | 12 | 12 | PASS ✓
NFR Tests Passed | 12 | 12 | PASS ✓
User Stories Fully Accepted | 12/12 | 12 | PASS ✓
Dashboard Load Time | 2.1s | < 3s | PASS ✓
Filter Response Time | 1.3s | < 1.5s | PASS ✓
Metric Accuracy vs Source | 0.04% | < 0.1% | PASS ✓
WCAG AA Color Contrast | Met | 4.5:1 | PASS ✓
Mobile Responsiveness (768px) | Met | 768px+ | PASS ✓
Time-to-Insight (avg) | < 25s | < 30s | PASS ✓
OPEN CHANGE REQUESTS (From UAT Sign-Off)
ID | Raised By | Tab | Priority | Request | Status
C-001 | Chloe Rivera | Tab 2 | Medium | Add % labels directly on funnel stage bars (not tooltip-only) | OPEN — next sprint
C-002 | Julie Chen | Tab 3 | High | Add YoY comparison toggle on donor trend chart | OPEN — Phase 2 (needs YoY data)
C-003 | Julie Chen | Tab 3 | Medium | Also flag gifts >$25k regardless of window average | OPEN — new calc field needed

## Deliverables Tracker
DELIVERABLES TRACKER — FUNDRAISING INTELLIGENCE DASHBOARD
Updated April 13, 2026 · Build start: April 15, 2026 · Target delivery: May 13, 2026
ID | Deliverable | Owner | Due Date | Status | Audience | Notes
D-01 | DARCI Matrix | PM | Apr 15 | COMPLETE ✓ | Internal + Client | Included in project documentation
D-02 | Business Requirements Document | BA | Apr 18 | IN PROGRESS | Internal | Use case + user stories complete
D-03 | Data Dictionary | BA | Apr 21 | COMPLETE ✓ | Internal + Client | 15 fields; signed off by Julie Chen
D-04 | Snowflake Analytics View (VW_FUNDRAISING_DASHBOARD) | Data Engineer | Apr 22 | NOT STARTED | Internal | Begins Apr 20
D-05 | Data Validation Report | Data Analyst | Apr 25 | NOT STARTED | Internal | Blocked until D-04
D-06 | CSV Extract (fundraising_extract_v1.csv) | Data Engineer | Apr 25 | NOT STARTED | Internal | Blocked until D-05
D-07 | Threshold Matrix (Excel) | BA | Apr 20 | IN PROGRESS | Int + Client | Workshop required Apr 18-19
D-08 | Wireframes — 3 tabs (PNG + PDF) | UX + BA | Apr 27 | COMPLETE ✓ | Int + Client | Signed off by Julie Chen + Chloe Rivera; Mar 15
D-09 | Tableau Calculation Library | BI Developer | Apr 28 | NOT STARTED | Internal | Blocked until D-06
D-10 | Dashboard — Executive Overview Tab | BI Developer | May 2 | NOT STARTED | Client | Blocked until D-09
D-11 | Dashboard — Campaign Performance Tab | BI Developer | May 4 | NOT STARTED | Client | Blocked until D-10
D-12 | Dashboard — Donor Intelligence Tab | BI Developer | May 6 | NOT STARTED | Client | Blocked until D-11
D-13 | QA Test Log (signed) | QA + Data Manager | May 9 | NOT STARTED | Internal | 51 FT + 12 NFR pre-defined
D-14 | UAT Plan & Results | BA | May 12 | NOT STARTED | Internal | 10 UAT scenarios pre-built
D-15 | Client Dashboard Guide (Word) | BA | May 13 | NOT STARTED | Client | Section 14 of project doc
D-16 | Full Project Documentation | BA + PM | May 13 | IN PROGRESS | Internal | v1.0 draft complete
D-17 | Published Tableau Public Link | BI Developer | May 13 | NOT STARTED | Client | Final gate: Data Manager approval
D-18 | User Training Session | BA | May 14 | NOT STARTED | Client | Julie + Chloe as primary participants

## KPI & Threshold Matrix
KPI DEFINITIONS & THRESHOLD MATRIX — FUNDRAISING INTELLIGENCE DASHBOARD
Thresholds validated with Julie Chen (Fundraising) & Chloe Rivera (Marketing) · March 15, 2026
KPI Name | Industry Baseline | Watch (Gold) | Warning (Coral) | Critical (Dark Red) | Direction | Tableau Calculation
Total Donations | $1.24M (2024) | — | — | — | ↑ Better | SUM([Donation_Amount])
Total Donors | 3,847 (2024) | — | — | — | ↑ Better | COUNTD([Donor_ID])
Average Gift | Varies by org | -5% | -10% | -15% | ↑ Better | AVG([Donation_Amount])
Repeat Donor Rate | 40–65% | -0.5 pt | -1.0 pt | -2.0 pt | ↑ Better | COUNTD(IF [Donated_More_Than_Once]='Yes' THEN [Donor_ID] END)/COUNTD([Donor_ID])
Email Open Rate | 20–30% | < 30% | < 25% | < 20% | ↑ Better | SUM(IF [Email_Opened]='Yes' THEN 1 ELSE 0 END)/COUNT([Email_ID])
Email Click Rate | 2–5% | < 5% | < 3% | < 2% | ↑ Better | SUM(IF [Email_Clicked]='Yes' THEN 1 ELSE 0 END)/COUNT([Email_ID])
Email Conversion Rate | 20–35% | < 30% | < 25% | < 20% | ↑ Better | SUM(IF [Email_Clicked]='Yes' THEN 1 ELSE 0 END)/SUM(IF [Email_Opened]='Yes' THEN 1 ELSE 0 END)
Campaign ROI | 2–4x | < 2.0x | < 1.5x | < 1.0x | ↑ Better | {FIXED [Campaign_ID]: MAX([Campaign_Cost])} → (SUM([Donation_Amount])-[CostDedup])/[CostDedup]
Avg Lifetime Value | Varies by org | — | — | — | ↑ Better | AVG([Lifetime_Giving])
Major Donor Concentration | 60% = concern | > 60% | > 65% | > 70% | ↓ Better | SUM(IF [Donor_Segment]='Major' THEN [Donation_Amount] END)/SUM([Donation_Amount])
Donor Growth YoY | 5–10% | < 5% | < 2% | Negative | ↑ Better | Year-over-year COUNTD
Outlier Flag | 2x window avg | — | — | > 2x or $25k | Signal | IF [Donation_Amount]>WINDOW_AVG(SUM([Donation_Amount]))*2 THEN 'Outlier' ELSE 'Normal' END
COLOR LEGEND: Navy = Stable ¦ Gold = Watch ¦ Coral = Warning ¦ Dark Red = Critical

## UAT Traceability Matrix
UAT TRACEABILITY MATRIX — USER STORIES TO WIREFRAME COMPONENTS
All 12 user stories passed · 51/51 functional tests passed · 12/12 NFR tests passed · March 15, 2026
Story ID | Tab | Wireframe Component | Business Persona | Test Cases | Validated By | Status
US-01 | Tab 1 | KPI Cards — Total Donations | Julie Chen | FT-01a–e | Julie Chen | PASS ✓
US-02 | Tab 1 | Donor Growth dual-axis chart | Julie Chen | FT-02a–e | Julie Chen | PASS ✓
US-03 | Tab 1 | Revenue by Channel bar | Julie + Chloe | FT-03a–e | Julie + Chloe | PASS ✓
US-04 | Tab 1 | Campaign ROI Ranking bar | Chloe Rivera | FT-04a–e | Chloe Rivera | PASS ✓
US-05 | Tab 1 | Insight Annotation Bar | Chloe Rivera | FT-05a–d | Chloe Rivera | PASS ✓
US-06 | Tab 2 | Email Engagement Funnel | Chloe Rivera | FT-06a–e | Chloe Rivera | PASS ✓
US-07 | Tab 2 | Cost vs. Revenue grouped bar | Julie + Chloe | FT-07a–e | Chloe + Julie | PASS ✓
US-08 | Tab 2 | Revenue by Campaign bar | Julie Chen | FT-08a–e | Julie Chen | PASS ✓
US-09 | Tab 3 | Donor Segmentation + Donut charts | Julie Chen | FT-09a–f | Julie Chen | PASS ✓
US-10 | Tab 3 | Geographic Donation Map | Julie Chen | FT-10a–e | Julie Chen | PASS ✓
US-11 | Tab 3 | Outlier scatter — Coral flag | Julie Chen | FT-11a–e | Julie Chen | PASS ✓
US-12 | Tab 3 | Lifetime Giving Distribution histogram | Chloe Rivera | FT-12a–e | Chloe Rivera | PASS ✓

## Project Plan (Gantt)
PROJECT PLAN — FUNDRAISING INTELLIGENCE DASHBOARD · Apr 15 – May 13, 2026
Task ID | Phase | Task Name | Owner | Start | End | Days | Status
T-01 | 1 – Initiation | Kickoff & DARCI assignment | PM | Apr 15 | Apr 15 | 1 | NOT STARTED
T-02 | 1 – Initiation | Requirements & stakeholder workshop | BA | Apr 15 | Apr 17 | 3 | NOT STARTED
T-03 | 2 – Requirements | Threshold definition workshop | BA + Stakeholders | Apr 18 | Apr 19 | 2 | NOT STARTED
T-04 | 2 – Requirements | KPI definitions & metric sign-off | BA | Apr 19 | Apr 19 | 1 | NOT STARTED
T-05 | 3 – Data Design | Data dictionary & field mapping | BA | Apr 19 | Apr 20 | 2 | NOT STARTED
T-06 | 3 – Data Design | Snowflake table + analytics view | Data Engineer | Apr 20 | Apr 22 | 3 | NOT STARTED
T-07 | 3 – Data Design | Data load & validation SQL | Data Engineer | Apr 22 | Apr 23 | 2 | NOT STARTED
T-08 | GATE 1 | Data Manager approval — data model | Data Manager | Apr 24 | Apr 24 | 1 | NOT STARTED
T-09 | 4 – BI Build | CSV extract export | Data Engineer | Apr 25 | Apr 25 | 1 | NOT STARTED
T-10 | 4 – BI Build | Tableau connection & field typing | BI Developer | Apr 26 | Apr 26 | 1 | NOT STARTED
T-11 | 4 – BI Build | Calculated fields implementation | BI Developer | Apr 26 | Apr 27 | 2 | NOT STARTED
T-12 | 4 – BI Build | Executive Overview tab build | BI Developer | Apr 27 | Apr 28 | 2 | NOT STARTED
T-13 | 4 – BI Build | Campaign Performance tab build | BI Developer | Apr 29 | May 1 | 3 | NOT STARTED
T-14 | 4 – BI Build | Donor Intelligence tab build | BI Developer | May 1 | May 3 | 3 | NOT STARTED
T-15 | GATE 2 | UX / BA wireframe alignment review | BA / UX | May 4 | May 4 | 1 | NOT STARTED
T-16 | 5 – QA | QA reconciliation & validation | QA / BA | May 5 | May 7 | 3 | NOT STARTED
T-17 | GATE 3 | Data Manager approval — metrics/gov | Data Manager | May 8 | May 8 | 1 | NOT STARTED
T-18 | 6 – UAT | UAT execution with stakeholders | BA / Stakeholders | May 9 | May 10 | 2 | NOT STARTED
T-19 | 7 – Deploy | Publish to Tableau Public | BI Developer | May 11 | May 12 | 2 | NOT STARTED
T-20 | 7 – Deploy | Deliver full documentation package | PM | May 12 | May 13 | 2 | NOT STARTED