## Project Plan & Gantt
Skye Data Advisory — Fundraising Intelligence Dashboard
Project Plan & Gantt Chart ¦ April 15 – May 13, 2026
ID | Phase | Task Name | Owner | Start | End | Days | Status | Deliverable | 4/15 | 4/16 | 4/17 | 4/18 | 4/19 | 4/20 | 4/21 | 4/22 | 4/23 | 4/24 | 4/25 | 4/26 | 4/27 | 4/28 | 4/29 | 4/30 | 5/1 | 5/2 | 5/3 | 5/4 | 5/5 | 5/6 | 5/7 | 5/8 | 5/9 | 5/10 | 5/11 | 5/12 | 5/13
T-01 | 1 – Initiation | Kickoff & DARCI assignment | PM | Apr 15 | Apr 15 | 1 | Not Started | DARCI Matrix
T-02 | 1 – Initiation | Requirements & stakeholder workshop | BA | Apr 15 | Apr 17 | 3 | Not Started | Business Requirements | bar: 4/15 to 4/17
T-03 | 2 – Requirements | Threshold definition workshop | BA + Stakeholders | Apr 18 | Apr 19 | 2 | Not Started | Threshold Matrix (Excel)
T-04 | 2 – Requirements | KPI definitions & metric sign-off | BA | Apr 19 | Apr 19 | 1 | Not Started | KPI Definition Doc | bar: 4/19
T-05 | 3 – Data Design | Data dictionary & field mapping | BA | Apr 19 | Apr 20 | 2 | Not Started | Data Dictionary
T-06 | 3 – Data Design | Snowflake table + analytics view | Data Engineer | Apr 20 | Apr 22 | 3 | Not Started | VW_FUNDRAISING_DASHBOARD | bar: 4/20 to 4/22
T-07 | 3 – Data Design | Data load & validation SQL | Data Engineer | Apr 22 | Apr 23 | 2 | Not Started | Data Validation Report
T-08 | GATE 1 | Data Manager approval — data model | Data Manager | Apr 24 | Apr 24 | 1 | Not Started | Signed Approval | bar: 4/24
T-09 | 4 – BI Build | CSV extract export | Data Engineer | Apr 25 | Apr 25 | 1 | Not Started | fundraising_extract_v1.csv
T-10 | 4 – BI Build | Tableau connection & field typing | BI Developer | Apr 26 | Apr 26 | 1 | Not Started | Connected workbook | bar: 4/26
T-11 | 4 – BI Build | Calculated fields implementation | BI Developer | Apr 26 | Apr 27 | 2 | Not Started | Calc Library
T-12 | 4 – BI Build | Executive Overview tab build | BI Developer | Apr 27 | Apr 28 | 2 | Not Started | Tab 1 worksheets | bar: 4/27 to 4/28
T-13 | 4 – BI Build | Campaign Performance tab build | BI Developer | Apr 28 | Apr 29 | 2 | Not Started | Tab 2 worksheets
T-14 | 4 – BI Build | Donor Intelligence tab build | BI Developer | Apr 29 | Apr 30 | 2 | Not Started | Tab 3 worksheets | bar: 4/29 to 4/30
T-15 | 4 – BI Build | Threshold color logic & parameters | BI Developer | Apr 29 | Apr 29 | 1 | Not Started | KPI status fields
T-16 | 4 – BI Build | Insight annotation panels | BI Developer | Apr 30 | Apr 30 | 1 | Not Started | Annotated tabs | bar: 4/30
T-17 | GATE 2 | UX + BA wireframe alignment review | BA + UX | May 01 | May 01 | 1 | Not Started | Wireframe sign-off
T-18 | 5 – QA | Data validation tests (DV-01–DV-10) | QA + BA | May 02 | May 03 | 2 | Not Started | QA Test Log | bar: 5/2 to 5/3
T-19 | 5 – QA | Calculation validation (CV-01–CV-08) | QA + BI Dev | May 03 | May 03 | 1 | Not Started | QA Test Log
T-20 | 5 – QA | Performance & stress tests (PT-01–PT-08) | BI Developer | May 04 | May 04 | 1 | Not Started | QA Test Log | bar: 5/4
T-21 | 5 – QA | Accessibility tests (AC-01–AC-04) | UX | May 04 | May 04 | 1 | Not Started | QA Test Log
T-22 | GATE 3 | Data Manager final approval | Data Manager | May 05 | May 05 | 1 | Not Started | Signed QA Log | bar: 5/5
T-23 | 6 – UAT | UAT plan execution with stakeholders | BA + Business | May 06 | May 08 | 3 | Not Started | UAT Results
T-24 | 6 – UAT | Change request resolution | BA + BI Dev | May 08 | May 08 | 1 | Not Started | CR Log | bar: 5/8
T-25 | 7 – Deploy | Publish to Tableau Public | BI Developer | May 10 | May 10 | 1 | Not Started | Dashboard URL
T-26 | 7 – Deploy | Client documentation package delivery | BA + PM | May 11 | May 11 | 1 | Not Started | Full Doc Package | bar: 5/11
T-27 | 7 – Deploy | User training session | BA | May 12 | May 12 | 1 | Not Started | Training Notes

## DARCI Matrix
DARCI Matrix — Fundraising Intelligence Dashboard
D = Driver ¦ A = Approver ¦ R = Responsible ¦ C = Consulted ¦ I = Informed
Role | Assigned To | Responsibilities | Deliverables | Distribution Timing
D — Driver | Project Manager | Owns project schedule and scope. Runs standups. Escalates blockers. Manages stakeholder communication. | Project Plan, Status Reports, Risk Log | Continuous
A — Approver | Data Manager | Signs off on data definitions, metric logic, governance compliance, extract contents, and QA results. No output distributed without approval. | Approval memos, signed QA Log, metric definition sign-off | Gates 1, 2, and 3
R — Responsible | BI Developer | Builds Snowflake analytics view, Tableau extract, calculated fields, dashboard sheets, and published workbook. | Working dashboard, Calculation Library, Sheet Spec | Per milestone
C — Consulted | Business Analyst | Leads requirements gathering, defines user stories, creates wireframe, manages UAT scenarios, authors project documentation. | BRD, User Stories, Wireframe, UAT Plan, Project Doc | Per milestone
C — Consulted | UX Designer | Applies Skye visual system to wireframe. Reviews dashboard layout, color usage, accessibility, and spacing before development. | Approved Wireframe PNGs, Visual System Guide | Gates 2
I — Informed | Nonprofit Stakeholders | Receive completed dashboard and client guide. Participate in UAT review session. Provide threshold calibration input in workshop. | Client Dashboard Guide, Dashboard URL, Training Session | UAT + Deploy phases
DISTRIBUTION PROTOCOL
Recipient | Deliverables Received
BI Developer | Full Internal Pack: project plan, data model, calc library, QA logs
Business Analyst | BRD, user stories, wireframe, UAT plan, threshold matrix
UX Designer | Wireframe spec, Skye visual system guide, dashboard layout spec
Stakeholders | Client Dashboard Guide, KPI definitions, threshold guide, dashboard link
Project Sponsor | Executive summary, Gantt milestone view, risk log

## Threshold Matrix
KPI Threshold & Alert Matrix
Complete during Threshold Definition Workshop (Days 3–4) ¦ Requires Data Manager approval before encode in Tableau
KPI Name | Industry Baseline | Client Baseline | Watch Threshold (Gold) | Warning Threshold (Coral) | Critical Threshold (Dark Red) | Direction | Dollar Impact / Pt | Action at Watch | Action at Warning | Action at Critical | Tableau Parameter Name | Workshop Confirmed By | Confirmed Date
Repeat Donor Rate | 40–65% | [TBD] | -0.5 pt change | -1.0 pt change | -2.0 pt change | Higher = Better | [TBD $/pt] | Monitor; prepare retention content | Investigate cause; plan re-engagement | Launch retention campaign immediately; target inactive 60–90 days | [P.RetentionWatch] | [Stakeholder]
Email Open Rate | 20–30% | [TBD] | < 30% | < 25% | < 20% | Higher = Better | [TBD] | Review send time and frequency | A/B test subject lines | Conduct list hygiene; audit sender reputation | [P.OpenRateWatch] | [Stakeholder]
Email Click Rate | 2–5% | [TBD] | < 5% | < 3% | < 2% | Higher = Better | [TBD] | Review CTA placement | Simplify email design | Redesign email template; realign offer | [P.ClickRateWatch] | [Stakeholder]
Email Conversion Rate | 20–35% | [TBD] | < 30% | < 25% | < 20% | Higher = Better | [TBD] | Review landing page | A/B test landing page | Simplify donation form; add urgency | [P.ConversionWatch] | [Stakeholder]
Campaign ROI | 2–4x | [TBD] | < 2.0x | < 1.5x | < 1.0x | Higher = Better | [TBD] | Investigate cost drivers | Restructure campaign; reduce spend | Pause campaign; reallocate budget | [P.ROIWatch] | [Stakeholder]
Donor Growth YoY | 5–10% | [TBD] | < 5% | < 2% | Negative | Higher = Better | [TBD] | Review acquisition channels | Launch acquisition push | Emergency acquisition strategy | [P.GrowthWatch] | [Stakeholder]
Major Donor Concentration | > 60% = concern | [TBD] | > 60% | > 65% | > 70% | Lower = Better | [TBD] | Begin mid-tier upgrade program | Accelerate diversification | Reduce dependency; emergency pipeline build | [P.ConcentrationWatch] | [Stakeholder]
Avg Gift Size | Varies by org | [TBD] | - 5% | - 10% | - 15% | Higher = Better | [TBD] | Review segment targeting | Adjust ask ladder | Redesign ask strategy; test new amounts | [P.AvgGiftWatch] | [Stakeholder]
WATCH | Early signal — monitor, prepare response
WARNING | Threshold crossed — investigate and plan action
CRITICAL | Immediate action required — escalate to leadership
STABLE | Within acceptable range — maintain current strategy

## KPI & Sheet Spec
KPI Definitions, Metrics & Dashboard Sheet Specification
For BI Developers and Data Analysts ¦ Version 1.0
SECTION A — KPI Definitions & Tableau Calculations
KPI Name | Business Definition | Tableau Calculation | Format | Dashboard Tab | Indicates | Visual Type | Color Rule
Total Donations | Sum of all donation amounts for the selected filter context. | SUM([Donation_Amount]) | $#,### | All Tabs | Overall revenue health — primary fundraising performance indicator. | KPI Card + Line | Threshold status color
Total Donors | Count of unique Donor_IDs in the selected context. | COUNTD([Donor_ID]) | #,### | All Tabs | Reach and breadth of engagement. Growing count = healthy acquisition. | KPI Card + Line | Navy stable; Coral if declining
Average Gift Size | Mean donation amount per transaction. | AVG([Donation_Amount]) | $### | All Tabs | Donor quality signal. Decline may indicate acquisition of lower-value donors. | KPI Card | Threshold status color
Repeat Donor Rate | Percentage of unique donors flagged as having donated more than once. | COUNTD(IF [Donated_More_Than_Once]="Yes" THEN [Donor_ID] END) / COUNTD([Donor_ID]) | 0.0% | Exec Overview, Donor Intel | Donor retention health. Declining rate signals relationship erosion. | KPI Card + Trend Line | Threshold: Watch/Warning/Critical color
Email Open Rate | Percentage of email recipients who opened the campaign email. | SUM(IF [Email_Opened]="Yes" THEN 1 ELSE 0 END) / COUNT([Email_ID]) | 0.0% | Campaign Perf. | Subject line and send-time effectiveness. | KPI Card + Funnel | Threshold status color
Email Click Rate | Percentage of recipients who clicked a link in the email. | SUM(IF [Email_Clicked]="Yes" THEN 1 ELSE 0 END) / COUNT([Email_ID]) | 0.0% | Campaign Perf. | Email content and CTA effectiveness. | KPI Card | Threshold status color
Email Conversion Rate | Of those who opened, what percentage clicked through. | SUM(IF [Email_Clicked]="Yes" THEN 1 ELSE 0 END) / SUM(IF [Email_Opened]="Yes" THEN 1 ELSE 0 END) | 0.0% | Campaign Perf. | Message-to-action effectiveness. Best single email efficiency metric. | Funnel + KPI Card | Threshold status color
Campaign ROI | Return on campaign spend using deduplicated cost per campaign. | {FIXED [Campaign_ID]: MAX([Campaign_Cost])} — use as [Campaign Cost Dedup] (SUM([Donation_Amount])-SUM([Campaign Cost Dedup]))/SUM([Campaign Cost Dedup]) | 0.0x | Campaign Perf. | Campaign efficiency. Below 1x = money-losing campaign. | Ranked Bar | Navy >2x; Gold 1–2x; Coral <1x
Avg Lifetime Value | Average lifetime giving amount across all donors in current context. | AVG([Lifetime_Giving]) | $#,### | Donor Intel | Long-term donor worth. High LTV segments deserve disproportionate stewardship. | Bar by Segment | Navy baseline
Major Donor Concentration | Revenue share contributed by Major segment donors. | SUM(IF [Donor_Segment]="Major" THEN [Donation_Amount] END) / SUM([Donation_Amount]) | 0.0% | Donor Intel | Concentration risk. Above 70% signals dangerous revenue dependency. | Donut / KPI Card | Threshold status color
Outlier Flag | Flags donations more than 2x the window average as outliers. | IF [Donation_Amount] > WINDOW_AVG(SUM([Donation_Amount]))*2 THEN "Outlier" ELSE "Normal" END | Text | All Tabs | Anomaly detection. Coral marks require investigation — positive or data error. | Color overlay | Coral = Outlier; Navy = Normal
SECTION B — Dashboard Sheet Specification
Sheet Name | Dashboard Tab | Chart Type | Rows/Dimensions | Columns/Measures | Filters | Calc Dependencies | Tooltip Content | User Story
KPI — Total Donations | Executive Overview | KPI Card | — | Total Donations | Date, Campaign, Segment | Total Donations | Value, change %, benchmark | US-01
KPI — Total Donors | Executive Overview | KPI Card | — | Total Donors | Date, Campaign | Total Donors | Value, change % | US-01
KPI — Avg Gift | Executive Overview | KPI Card | — | Average Gift | Date, Campaign | Average Gift | Value, benchmark | US-01
KPI — Repeat Donor Rate | Executive Overview | KPI Card w/ color | — | Repeat Donor Rate | Date | Repeat Donor Rate, Retention Status | Value, threshold status, dollar impact | US-02
KPI — Campaign ROI (Exec) | Executive Overview | KPI Card | — | Campaign ROI | Date | Campaign ROI, Campaign Cost Dedup | Best/worst campaign | US-03
Donations Over Time | Executive Overview | Line Chart | Donation Month | Total Donations | Date, Channel, Segment | Total Donations | Month, revenue, % change | US-04
Exec Insight Panel | Executive Overview | Text / Annotation | — | — | — | Retention Status, Outlier Flag | Recommended action text | US-05
Campaign Revenue Ranking | Campaign Perf. | Horizontal Bar | Campaign | Total Donations | Date, Channel, Geography | Total Donations | Campaign, revenue, rank | US-06
Email Funnel | Campaign Perf. | Funnel | Stage | Count | Date, Campaign | Email Open Rate, Click Rate, Conversion Rate | Stage, count, drop-off % | US-07
Campaign Cost vs Revenue | Campaign Perf. | Grouped Bar | Campaign | Total Donations + Campaign Cost Dedup | Date, Channel | Campaign ROI, Campaign Cost Dedup | Revenue, cost, ROI | US-08
Revenue by Channel | Campaign Perf. | Bar | Channel | Total Donations | Date, Campaign | Total Donations | Channel, revenue, % total | US-09
KPI — Email Conversion | Campaign Perf. | KPI Card w/ color | — | Email Conversion Rate | Date, Campaign | Email Conversion Rate, status | Rate, threshold status | US-10
Donor Segmentation | Donor Intel | Donut Chart | Donor_Segment | Total Donations | Date, Geography | Major Donor Concentration | Segment, revenue, % total | US-11
Lifetime Value by Segment | Donor Intel | Bar | Donor_Segment | Avg Lifetime Value | Date | Avg Lifetime Value | Segment, LTV, count | US-12
Repeat vs New Trend | Donor Intel | Dual Line | Donation Month | Repeat Count + New Count | Date, Segment | Repeat Donor Rate | Month, repeat, new, total | US-13
Geographic Map | Donor Intel | Filled Map | Geography | Total Donations | Date, Campaign, Segment | Total Donations | State, revenue, donor count | US-14
Outlier Donors | Donor Intel | Scatter / Detail Table | Donor_ID | Donation Amount | Date, Campaign | Outlier Flag | Donor, amount, outlier flag | US-15

## Deliverables Tracker
Deliverables Tracker — Fundraising Intelligence Dashboard
Updated by PM ¦ Reviewed at every standup
ID | Deliverable | Owner | Due Date | Status | Audience | Format | Location / Link | Notes
D-01 | DARCI Matrix | PM | Apr 15, 2026 | Not Started | Internal + Client | Excel Tab | Project workbook | Distribute after kickoff
D-02 | Business Requirements Document | BA | Apr 18, 2026 | Not Started | Internal | Word | Project folder | Basis for all build decisions
D-03 | Data Dictionary | BA | Apr 21, 2026 | Not Started | Internal + Client | Word Section 5 | Project Doc | Requires Data Manager review
D-04 | Snowflake Analytics View | Data Engineer | Apr 22, 2026 | Not Started | Internal | Snowflake DDL | FUNDRAISING_DB.ANALYTICS | VW_FUNDRAISING_DASHBOARD
D-05 | Data Validation Report | Data Analyst | Apr 25, 2026 | Not Started | Internal | Word / Excel | QA folder | Baseline for all reconciliation
D-06 | CSV Extract (v1) | Data Engineer | Apr 25, 2026 | Not Started | Internal | CSV | /extracts/ | fundraising_extract_v1.csv
D-07 | Threshold Matrix (Excel) | BA | Apr 20, 2026 | Not Started | Internal + Client | Excel Tab | Project workbook | Workshop required before completion
D-08 | Wireframe — 3 tabs (PNG) | UX + BA | Apr 27, 2026 | Complete | Internal + Client | PNG | Design folder | 3 PNGs per earlier session
D-09 | Tableau Calculation Library | BI Developer | Apr 28, 2026 | Not Started | Internal | Word Section 7 | Project Doc | Must match data dictionary definitions
D-10 | Dashboard — Executive Overview Tab | BI Developer | May 2, 2026 | Not Started | Client | Tableau | Tableau Public | Includes KPI cards + insight panel
D-11 | Dashboard — Campaign Performance Tab | BI Developer | May 4, 2026 | Not Started | Client | Tableau | Tableau Public | Includes email funnel + ROI chart
D-12 | Dashboard — Donor Intelligence Tab | BI Developer | May 6, 2026 | Not Started | Client | Tableau | Tableau Public | Includes map + segmentation
D-13 | QA Test Log (signed) | QA + Data Manager | May 9, 2026 | Not Started | Internal | Excel | QA folder | Data Manager sign-off required
D-14 | UAT Plan & Results | BA | May 12, 2026 | Not Started | Internal | Word | Project folder | 10 scenarios per Section 11
D-15 | Client Dashboard Guide | BA | May 13, 2026 | Not Started | Client | Word | Client folder | Plain-language; extract from Section 14
D-16 | Full Project Documentation | BA + PM | May 13, 2026 | In Progress | Internal | Word | Project folder | This document
D-17 | Published Tableau Public Dashboard | BI Developer | May 13, 2026 | Not Started | Client | URL | tableau.com | Final client URL shared by PM
D-18 | User Training Session | BA | May 14, 2026 | Not Started | Client | Meeting | — | 60-minute walkthrough with stakeholders

## Risk Log
Risk Log — Fundraising Intelligence Dashboard
Owner updates weekly ¦ PM reviews at standup ¦ Escalate Critical risks to Data Manager
ID | Risk Description | Category | Likelihood | Impact | RAG | Owner | Mitigation | Status | Notes
R-01 | Campaign_Cost duplication inflates ROI if not deduplicated at row level. | Data Quality | High | High | R | BI Dev | Use FIXED LOD {FIXED [Campaign_ID]: MAX(Campaign_Cost)} in all ROI calcs. Validate in CV-04. | Open | LOD must be QA'd against Snowflake SQL
R-02 | Email metrics misinterpreted — click rate vs. conversion rate confused by users. | Communication | Medium | Medium | A | BA | Add tooltip definitions; include glossary in client guide (Section 14). | Open | Include in user training session
R-03 | Threshold values not validated with stakeholders before encode in Tableau. | Requirements | Medium | High | R | BA | Conduct threshold workshop Day 3–4; document all values in Excel Threshold Matrix tab. | Open | Workshop required as Gate condition
R-04 | Tableau Public extract goes stale with no automated refresh process. | Operations | High | Medium | A | Data Manager | Document manual refresh cadence in governance section; note Tableau Public limitation to client. | Open | Consider Tableau Server for production
R-05 | Major donor concentration > 70%: single departure creates revenue cliff. | Business | Low | High | A | Dev Director | Surface in Major Donor Concentration KPI with critical threshold. Flag in insight panel. | Open | Monitor closely at UAT
R-06 | September donor spike is a data anomaly, not a real performance trend. | Data Quality | Low | Medium | G | Data Analyst | Annotate spike in dashboard; add attribution validation note in insight panel. | Open | Validate before publish
R-07 | Dashboard published with real donor PII if synthetic data is replaced without governance review. | Compliance | Low | Critical | R | Data Manager | Data Manager must verify dataset composition before any extract is promoted to Tableau Public. | Open | Hard gate — no exceptions
R-08 | Stakeholder threshold preferences not captured before development begins. | Requirements | Medium | High | R | BA | Threshold workshop is a mandatory checklist item (T-03). No BI build begins until complete. | Open | Block BI build if workshop not done